## Cover Page
Online Tailoring Store
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Academy - Project solutions
Role
Signature
| Date | 2019-11-20
Project ID: B023 |  |  |  | <SCI.ID> / Ver: V 1.0
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog Online Tailoring Store Project ID: B023 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | User Registration | User (Customer / Tailor) | As a user, I should be able to register to this website | 1. Clicking on the “Register” button should open the Registration form. 2. User to fill the basic attributes: First Name Last Name DoB Gender Contact Number Category User Id Password 3. Clicking ‘Submit’ button should validate the datatype constraints for each field 4. User failing to provide information for the mandatory fields be presented with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5. Post-successful field validation, save the information in the database 6. Upon saving the information in the database, display the message “New user created successfully” | 1 | 5 | Yes | 1 | 1 | 5
US_2 | User Authentication | User | As a user, I should be able to log in | 1. Clicking “Sign In” link should allow the user to enter the User ID and Password and click 2. Portal to validate the entered user credentials against the database and allow login for registered users. 3. If User ID is not present, it should throw error saying " User ID not present. For wrong password, it should say "Password not matching" | 1 | 2 | Yes | 1 | 1 | 2
US_3 | Admin credentials | Admin | As a Admin, I should be able to log in | 1. System should have a User Login credentials stored in the DB. 2. When keyed in with correct credentials, it should log in. 3. If User ID is not present, it should throw error saying " User ID not present. For wrong password, it should say "Password not matching" | 1 | 2 | Yes | 1 | 1 | 2
US_4 | Log off | User | As a user, I should be able to log off | 1. When the user clicks Log off, the system should disconnect from the system. | 1 | 2 | Yes | 1 | 1 | 2
US_5 | Add Category | Admin | As an admin, I should be able to add the categorys | 1. On clicking Add category, it should allow me to add categorys. Men / Women/ Boys / Girls 2. On clicking submit, it should validate and save the details to the DB. 3. Appropriate message should be displayed. | 1 | 2 | Yes | 1 | 1 | 2
US_6 | Add Dress type | Admin | As an Admin I should be able to add all possible dress types | 1. On clicking Add Dress type, it should allow me to add dress types. Eg Shirt, Pant, Kurti, Salwar, Blouse, etc. 2. Each dress type should be mapped to the category 3. On clicking submit, it should validate and save the details to the DB. 4. Appropriate message should be displayed. | 1 | 5 | Yes | 1 | 1 | 5
US_7 | Dress Type | Tailor | As a tailor, I should be able to select the type of dress I can stitch | 1. On clicking dress type, it should list all the type of dresses possible from the DB. 2. Tailor can select all dresses he can stitch 3. Catagorisation like Men / Women/ Boys / Girls should be there. 4. Dress type should be mapped to the category. | 1 | 3 | Yes | 1 | 1 | 3
US_8 | Update Patterns / cost | Tailor | As a tailor , I should be able to upload patterns and update cost. | 1. On clicking upload pattern, it should list all the type of dresses, the tailor can stitch. 2. On selecting the type, tailor should be able to upload the images/ patterns. 3. The cost of each pattern should be updated. 4. On clicking Submit, the details will be saved after validation. 5. Appropriate messages should be displayed. | 1 | 5 | Yes | 1 | 1 | 5
US_9 | Update Details | Tailor | As a tailor, I should be able to update my details / profile | 1. On clicking Update details, it should redirect to the Details page. 2. Tailor can update the name of the shop, Address, Contact number, Working hours, Available services etc. If courier option is there, that needs to be mentioned. 3. On submitting, the details should be validated and saved to the DB. 4. Corresponding message should be displayed. | 1 | 3 | Yes | 1 | 1 | 3
US_10 | Search tailor | Customer | As a customer, I should be able to search for tailor. | 1. ON clicking search tailor, to should redirect to the Tailor Search page. 2. Customer, should be able to select category 3. Customer should be able to select Dress type 4. Customer should be able to enter Area - This field can be optional for the customer who prefers courier. 5. On clicking search, system should list the tailors in that area who will stitch, the selected dress type for the selected category. 6. If customer selects courier option, records matching to that should be displayed. | 2 | 5 |  | 2 | 2 | 5
US_11 | View Tailor Details | Customer | As a customer I should be able to view details | 1. On clicking each tailor ID, the tailor details should be displayed. 2. Customer should be able to view all the patterns uploaded by the tailor. 3. He can view the cost for each patterns. 4. Additional details entered should be viewed. 5. He should be able to view the reviews and ratings if available. | 2 | 5 |  | 2 | 2 | 5
US_12 | Place Orders | Customer | As a customer I should be able to place orders | 1. Customer is able to access the Make Order page post the successful validation of the customer credentials 2. To make order,customer should provides the details of the garments. 3. He should select the type of dress to be stiched and provide measurments of the garments. 4. For Top measurments he should provide data like fabric,material type, duration, Toplengths, amout, neck, topwaist, chest, shoulder length 5. For Bottom measurments he should provide data like fabric, material type, duration, Bottmlength, amout, hip, Kneelength 6. Clicking ‘Submit ,It should get updated in admin’s view customers orders list page. 7. Customer can also update the expected date of delivery. 8. Customer should be able to select patterns from the gallery 9. Customer can give any additional comments. | 2 | 8 |  | 2 | 2 | 8
US_13 | View orders | Tailor | As a tailor, I should be able to view orders. | 1. On clicking View Orders, it should redirect to the orders page. New orders. Active orders Completed Orders. 2 Tailor can select any one. 3. Clicking Active orders, should display all the active orders. 4. Clicking Completed orders, should display all the completed orders. 5. Clicking New orders, should list all the new orders. 6. Clicking the order ID, tailor should be able to view the details. | 2 | 5 |  | 2 | 2 | 5
US_14 | Accept orders | Tailor | As a tailor, I should be able to accept orders. | 1. After viewing the details, tailor can accept the orders. 2. If any update to be made to the date of delivery or pattern, he should be able to do it. (Assumption is that tailor will discuss this over the phone with customer) | 2 | 5 |  | 2 | 2 | 5
US_15 | Bill generation | SYstem | As a system, I should be able to generate bill |  | 2 | 8 |  | 2 | 2 | 8
US_16 | View status | Customer | As a customer, I should be able to view status | 1. Clicking orders, should list all the active orders at the top and history at the bottom. 2. By clicking order ID I should be able to view the details. Status of the order, Bill amount etc | 2 | 1 |  | 2 | 2 | 1
US_17 | Update status | Tailor | As a tailor, I should be able to update the status | 1. On clicking Active orders, it should list all the accepted active orders. 2. Tailor can update the status. 3. If to be couriered it can be updated. 4. Any delays or change in pattern should also be updated. | 2 | 3 |  | 2 | 2 | 3
US_18 | Payment | Customer | As a customer, I should be able to make payment | 1. When courier option is selected, Customer should make payment. 2. On payment only tailor will courier 3. In person delivery, customer can select Card payment or Cash on delivery. 4. When paid status should be reflected in the order. | 2 | 5 |  | 2 | 2 | 5

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000