## Cover Page
Online Tailoring Store
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Aakash Chaudhari
Role
Signature
| Date | 2020-03-06
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store registration details |  | Trainee_1 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_2 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_1 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_2 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog Online Tailoring Store Project ID: B023 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | User Registration | 5
Task_1 | Create table to store registration details |  | Dipak |  | 4 | 2 | 1 | 1 | 0 | 0
Task_2 | Design the registration page |  | Paresh |  | 3 | 2 | 1 | 0 | 0 | 0
Task_3 | Develop Code for Validation of Form Field |  | Adesh |  | 2 | 1 | 1 | 0 | 0 | 0
Task_4 | Develop Code for Store User Data in database |  | Aakash |  | 3 | 2 | 0 | 1 | 0 | 0
User Story #2 | User Authentication | 2
Task_1 | Develop code for Validating Enter Username and Password from Database |  | Adesh |  | 3 | 1 | 0 | 0 | 0 | 0
User Story #3 | Admin Credentials | 2
Task_1 | Develop code for Validating Enter Admin Username and Password from Database |  | Aakash |  | 2 | 0 | 1 | 0 | 0 | 0
User Story #4 | Log off | 2
Task_1 | Develop code for - On Log off, It should be disconnect connection |  | Paresh |  | 3 | 1 | 1 | 1 | 0 | 0
User Story #5 | Add Category | 2
Task_1 | Develop code for - On Add Category should be store in Database with valid input check |  | Dipak |  | 2 | 0 | 0 | 1.5 | 0 | 0
User Story #6 | Add Dress Type | 5
Task_1 | Develop Code for - On clicking Add Dress Type should be store in database with validation check |  | Dipak |  | 2 | 1 | 0 | 1 | 0 | 0
Task_2 | Develop Code for Message Display when it will store data in Database |  | Aakash |  | 1 | 0.5 | 0 | 0 | 0 | 0
User Story #7 | Dress Type | 3
Task_1 | Develop code for - On clicking Dress Type it should list all the type of dresses |  | Paresh |  | 2 | 1 | 0 | 1 | 0 | 0
Task_2 | Develop code for Dress Type should be mapped to the Category |  | Dipak |  | 3 | 1 | 0 | 1 | 0 | 0
User Story #8 | Update Patterns/ Cost | 5
Task_1 | Develop code for - On clicking Upload Pattern, it should list all the type of dressed, the tailor can stitch |  | Aakash |  | 4 | 2 | 1.5 | 0.5 | 0 | 0
Task_2 | Develop code for - On Selecting the type, tailor should be able to upload image/pattern with store in Database |  | Paresh |  | 3 | 0 | 2 | 1 | 0 | 0
User Story #9 | Update Details | 3
Task_1 | Develop Code for - On Clicking Update Details, it should redirect to Details Page |  | Dipak |  | 1 | 0 | 1 | 0 | 0 | 0
Task_2 | Develop Code for take input fields from Tailor for update details with validation check after it will store data in database |  | Dipak |  | 2 | 0 | 1 | 1 | 0 | 0
TOTAL |  |  |  |  | 40 | 14.5 | 10.5 | 10 | 0 | 0

## Sprint -2
Sprint Backlog Online Tailoring Store Project ID: B023 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #10 | Search tailor | 5
Task_1 | Develop Code for - On clicking search tailor, it should be redirect to the Tailor Search Page and show the list of tailors |  | Aakash |  | 2 | 1 | 1 | 0 | 0 | 0
User Story #11 | View Tailor Details | 5
Task_1 | Develop Code for - On Clicking each tailor id, the tailor details should be displayed |  | Dipak |  | 2 | 0 | 1 | 1 | 0 | 0
Task_2 | Develop Code for view Reviews |  | Paresh |  | 2 | 1 | 0 | 1 | 0 | 0
User Story #12 | Place Orders | 8
Task_1 | Develop Code for make order page |  | Adesh |  | 2 | 1 | 0 | 1 | 0 | 0
User Story #13 | Views Orders | 5
Task_1 | Develop Code for On clicking View Orders |  | Aakash |  | 2 | 1 | 0 | 0.5 | 0 | 0
Task_2 | Develop Code for On clicking Active Orders, Completed Orders, New orders it should show respective orders |  | Adesh |  | 2 | 0 | 1.5 | 0.5 | 0 | 0
User Story #14 | Accept Orders | 5
Task_1 | Develop Code for tailor can accept Orders |  | Aakash |  | 2 | 1 | 0 | 1 | 0 | 0
Task_2 | Develop Code for any update of delivery to be made in Database |  | Dipak |  | 1 | 0 | 0.5 | 1 | 0 | 0
User Story #15 | Bill Generation | 8
Task_1 | Develop Code for system generate the bill |  | Paresh |  | 5 | 2 | 2 | 1 | 0 | 0
Task_2 | Develop Code for update the bill amount if required |  | Dipak |  | 3 | 1 | 1 | 1 | 0 | 0
User Story #16 | View Status | 1
Task_1 | Develop Code for on Clicking orders, should list all the active orders at top and history at bottom |  | Adesh |  | 3 | 0 | 1.5 | 1.5 | 0 | 0
Task_2 | Develop Code for on clicking order ID, it should be able to view the details |  | Adesh |  | 2 | 1 | 1 | 0 | 0 | 0
User Story #17 | Update Status | 3
Task_1 | Develop Code for - On clicking Active orders, it should list all the accepted active orders |  | Aakash |  | 1 | 0 | 1 | 0 | 0 | 0
User Story #18 | Payment | 5
Task_1 | Develop Code for when courier option is selected, Customer should make payment |  | Dipak |  | 2 | 0 | 1.5 | 1 | 0 | 0
Task_2 | Develop Code for customer can select Card payment or Cash on delivery |  | Paresh |  | 2 | 1 | 1 | 0.5 |  | 0
TOTAL |  |  |  |  | 33 | 10 | 13 | 11 | 0 | 0

## Sprint -3
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1
Task_1
Task_2
Task_3
Task_4
User Story #2
Task_1
Task_2
Task_3
Task_4
User Story #3
Task_1
Task_2
Task_3
Task_4
User Story #4
Task_1
Task_2
Task_3
Task_4
User Story #5
Task_1
Task_2
Task_3
Task_4
TOTAL |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Data (hidden)
In-Progress
Completed
N/A